## Sheet1
java ファイル
| 画面 | jsp | ａｃｔｉｏｎ | dao | dto | 進捗 | 担当
1 | ヘッダー | header.jsp | header.action | header.dao | header.dto | 50% | 古長
2 | フッター | footer.jsp | footer.action | footer.dao | footer.dto | 75% | 古長
3 | メイン | main.jsp | main.action | main.dao | main.dto | 75% | 古長
4 | ログイン | login.jsp | login.action | login.dao | login.dto | 75% | 植松
5 | 新規登録 | user_apply.jap | user_apply.action | user_apply.dao | user_apply.dto | 75% | 植松
6 | ジャンルセレクト | select.jsp | select.action | select.dao | select.dto | 75% | 李
7 | サイト記事 | article.jsp | article.action | article.dao | article.dto | 75% | 李
8 | 管理人 | admin_top.jsp | admin_top.action | admin_top.dao | admin_top.dto | 75% | 伊藤
9 | ユーザー管理 | admin_user.jsp | admin_user.action | admin_user.dao | admin_user.dto | 60% | 植松
10 | レビュー管理 | admin_review.jsp | admin_review.action | admin_review.dao | admin_review.dto | 75% | 前田
11 | サイト記事管理 | admin_article.jsp | admin_article.action | admin_article.dao | admin_article.dto | 75% | 李
12 | ユーザー | user_top.jsp | user_top.action | user_top.dao | user_top.dto | 75% | 伊藤
13 | ユーザー情報変更 | user_info_edit.jsp | user_info_edit.action | user_info_edit.dao | user_info_edit.dto | 75% | 植松
14 | レビュー履歴 | user_review.jsp | user_review.action | user_review.dao | user_review.dto | 75% | 前田
15 | AboutUs | about_us.jsp | about_us.action | about_us.dao | about_us.dto | 75% | 伊藤
16 | ContactUs | contact_us.jsp | contact_us.action | contact_us.dao | contact_us.dto | 75% | 伊藤
機能・画面実装進捗平均 | [5 empty] | 72.5%